## Plan
Plan ID | Plan name | Date of export
aOKYgJ56GEKfUyDEM43VlcgABv1k | Week 4 - project : Team 13 | 2026-08-15

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
3EHNdJOPI023mvhTQzxdE8gACXL_ | [BOOTSTRAP RESTYLING] - Write requirements for team page + login styling : 60 | Done |  | Completed | Important | Hiep Vu | Khac Tung Lam Nguyen | 2026-08-04 | 2026-08-07 | 2026-08-07 |  | false | 2026-08-07 | Khac Tung Lam Nguyen | 5/5 | Edge cases documented;Requirements shared with PM and UX;Login scope explicitly stated as styling-only;Document updated;Team page fields listed with validation/display rules | BA;Sprint 1 | Description Determine the content fields for the team page (name, photo, role, blurb) and confirm the login work is styling only, with no changes to existing auth logic or session behavior. Document edge cases such as missing photos or long blurb text. Done I wrote and finalized functional, non-functional requirements, user stories and acceptance criteria for the login page(styling-only) and team page (also edge cases). Deliverable Document is updated at https://github.com/emeralddd/capstone-boilerplate/blob/main/docs/login_restyling.docx or login_restyling.docx Note For the UX, the team branding color palette and typography are not defined yet - UX needs to confirms these before Dev start styling.
pkIqu5vHwUWaC1vjHRinZ8gAMFpO | [BOOTSTRAP RESTYLING] - Design Login Style & Team Page Layout :120 | Done |  | Completed | Medium | Marcell Joe Sugianto | Khac Tung Lam Nguyen | 2026-08-04 | 2026-08-09 | 2026-08-08 |  | false | 2026-08-09 | Khac Tung Lam Nguyen | 5/5 | Document Updated;Design shared with BA for validation;Visual consistency between the two checked;Login page mockup complete;Team page mockup complete | UX;Sprint 1 | Description Produce a mockup design of the Teams and Login page. The Teams page must display all team members in a fixed order (PM, BA, UX, Dev 1, Dev 2), and each should display the name, picture, role and blurb of the member. Unavailabe information should have a placehoder in place. If the data for the members is unavailable, display "No team members yet" The login page should have a consistent style with the Teams page, and have a validation message. The pages should have responsive designs for various screen sizes Done I made a mockup design of the Teams and Login page as per sepcification, and have created some assets used in the designs. Deliverables Design: https://www.figma.com/design/JnkORkFEkRuspZS0keT8zl/Capstone?node-id=0-1&t=XG9H1VO4tKxsCIFS-1 Assets: https://www.figma.com/design/JnkORkFEkRuspZS0keT8zl/Capstone?node-id=0-1&t=XG9H1VO4tKxsCIFS-1 Note to next role The color palette used for the designs is in the "Palette" page of the FigmaDesign file. I've also pushed the assets and the design link on GitHub Asset: ./frontend/assets/ Design link: ./docs/FigmaDesign_Link.md
879IK850MEa4K9OwQP9yS8gAIEqa | [BOOTSTRAP RESTYLING]- Validate Design Against Requirements : 60 | Done |  | Completed | Medium | Hiep Vu | Khac Tung Lam Nguyen | 2026-08-04 | 2026-08-10 | 2026-08-10 |  | false | 2026-08-10 | Khac Tung Lam Nguyen | 5/5 | Login scope confirmed unchanged;Every required field checked against the design;Design formally approved;Document Updated;Gaps (if any) sent back to UX and resolved | BA;Sprint 1 | Description Check the UX mockups against the requirements document. Confirm every field is represented, the login mockup stays styling-only, and edge cases have a visible design treatment. Flag any gaps back to UX before approving. Done I have checked UX design and validated to make sure it consistent with the requirement. Delivery Document is updated at login_restyling.docx
N7LdQjWP6E6n2h3AdqGsb8gAGYlH | [BOOTSTRAP RESTYLING] - Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only : 60 | Done |  | Completed | Medium | Rhys Carroll | Khac Tung Lam Nguyen | 2026-08-04 | 2026-08-12 | 2026-08-12 |  | false | 2026-08-12 | Rhys Carroll | 4/4 | Existing login validation/errors still function as before;No authentication logic changed;Update document;Visual style matches approved mockup | DEV;Sprint 1 | Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only. Done: Applied the approved login styling (colors, layout, branding). Confirmed auth logic, validation, and session handling are all untouched. Styling scales to different screen sizes too. Deliverable: Branch/commit with the styling changes. Note for next role: Preexisting assets inside of frontend/components/layout/auth can be reused for teams page, team page member card had incomplete draft component created, current dashboard should be reworked into team's page and normal dashboard changed back, kept as is to keep progress. Git URL (commit): https://github.com/emeralddd/capstone-boilerplate/commit/df4749981957bca520db80d084914fbf90b42ec5
MeHPv9W4PEmKvvOAGyj1kMgAE5ZJ | [BOOTSTRAP RESTYLING]- Build Team Page & Auth Redirect : 120 | Done |  | Completed | Medium | Kieran Chau | Khac Tung Lam Nguyen | 2026-08-04 | 2026-08-13 | 2026-08-13 |  | false | 2026-08-12 | Kieran Chau | 4/4 | Team page renders per design with all required fields;Successful login redirects to team page;Document updated;Team page not directly accessible without login | DEV;Sprint 1 | Build the team page per the approved design (name, member cards, blurb) and wire it so a successful login redirects the user here. The team page itself should not be reachable without a valid login. Done: Cleaned up dashboard Restyled team page per UI specification Ensured that team page is automatically redirected to after successful login, otherwise it is not accessible Deliverable: https://github.com/emeralddd/capstone-boilerplate/commit/895bb5511319a31d063a22bd2e90db4dbac72fd8 Note for next role: Team member cards are hardcoded, do we want that? And the profile photo initials are too, cannot currently put a picture inside (if that's something we want).
lGvvAuXx-kuLv7gBk4oTAsgACobb | [BOOTSTRAP RESTYLING] - Deploy - 120 | Done |  | Completed | Medium | Kieran Chau | Khac Tung Lam Nguyen | 2026-08-04 | 2026-08-13 | 2026-08-13 |  | false | 2026-08-13 | Kieran Chau | 4/4 | Live URL loads without errors;Document updated;Deployment completed via boilerplate pipeline;Login → redirect → team page flow spot-checked on the deployed URL | DEV;Sprint 1 | Deploy the updated application (restyled login + team page + redirect) using the boilerplate's deployment pipeline. Confirm the deployed version is live and functioning before handing off to Dev 2. Done: Deployed website to Vercel. Deliverable: Link to website: https://capstone-boilerplate-frontend.vercel.app/ . Note for next role: None.
Oy3hDXBGnkKzwfWiCtOmdsgAGsaF | [BOOTSTRAP RESTYLING] - Test Login → Redirect → Team Page Flow : 60 | Done |  | Completed | Medium | Rhys Carroll | Khac Tung Lam Nguyen | 2026-08-04 | 2026-08-13 | 2026-08-13 |  | false | 2026-08-13 | Rhys Carroll | 4/4 | All required content verified correct and complete;Document updated;Redirect to team page confirmed;Valid login tested end-to-end on deployed URL | DEV;Sprint 1 | On the deployed URL (not localhost if possible) , test the full happy-path flow: valid login, redirect to team page, and all required content displaying correctly. Must not be the same dev who built this feature. Done: Manually tested the full happy path on the deployed URL — valid login, redirect fires, all member cards render correctly with photo/role/blurb. Note for next role: Name Rhys Carroll is spelt wrong, as "Rhys Carrol" should be "Rhys Carroll
NmKLq2vGmUm_jHzOZSUtTsgAAuUp | [BOOTSTRAP RESTYLING] - Test Edge Cases & Log Bugs : 60 | Done |  | Completed | Medium | Rhys Carroll | Khac Tung Lam Nguyen | 2026-08-04 | 2026-08-13 | 2026-08-13 |  | false | 2026-08-13 | Rhys Carroll | 5/5 | Missing-photo and long-blurb edge cases tested;Update Document;Invalid login tested;Bugs logged with repro steps, or none-found confirmed;Direct team-page access without login tested (must redirect) | DEV;Sprint 1 | Test edge cases identified by the BA: invalid login, direct team-page access without logging in, a missing photo, and an unusually long blurb. Log any bugs found back to Dev 1 with reproduction steps. Done: Tested invalid login, direct team-page URL access without login, missing-photo member, and an unusually long blurb. No bugs found. Note for next role: Unusually long blurb missing “see more” feature, just continues expanding component size.
TBxbGig6aE61zzFxCI0Pi8gAA5Do | [BOOTSTRAP RESTYLING] - Final Review & Sign-Off : 30 | Done |  | Completed | Medium | Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-04 | 2026-08-15 | 2026-08-15 |  | false | 2026-08-15 | Khac Tung Lam Nguyen | 3/3 | Feature reviewed end-to-end against requirements and design;All prior tasks' checklists verified complete;Task moved to Done | PM;Sprint 1 | PM reviews the completed feature end-to-end against the original requirements and design, confirms every prior task's checklist is complete, and signs off. Done: Reviewed the feature end-to-end against the requirements and design. Verified every prior task's checklist and completion comment. Everything matches — approved. Deliverable: Sign-off note. Note for next role: None — feature complete, board closed out.
8xLXAGrVbkCiy11TOMZjQsgACJTm | [BOOTSTRAP RESTYLING] - Internal Team Meeting : 30 | Done |  | Completed | Medium | Hiep Vu;Kieran Chau;Marcell Joe Sugianto;Rhys Carroll;Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-07 | 2026-08-05 | 2026-08-05 |  | false | 2026-08-07 | Khac Tung Lam Nguyen | 5/5 | Set internal deadlines for each task;Assign the tasks (especially for Dev 1 and Dev 2);Prepare for client meeting;Confirm the role for this sprint;Confirm the flow of task card on Planner | PM;UX;DEV;BA;Sprint 1 | This is the Planning Session Meeting for this sprint. Done: Introduction about each member and task assignments for demo sprint. Deliverable: Meeting Minutes: 2026-08-06_MiniSprint Planning Session.docx Note for next role: Work on each member task based on assignments.
S9Xsp7LO9UGlbeZUE8z14sgAEVWO | [PROJECT PROTOTYPING] - First Client Meeting : 30 | Done |  | Completed | Medium | Hiep Vu;Kieran Chau;Marcell Joe Sugianto;Rhys Carroll;Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-10 | 2026-08-10 | 2026-08-10 |  | false | 2026-08-11 | Khac Tung Lam Nguyen | 1/1 | Gather requirements from client | PM;UX;DEV;BA | Meet with the client to get the requirements and instructions for the project. Done: We met with Alessio to get information about the project. Deliverable: Meeting Minutes: 2026-08-10_Client Meeting Session Copy.docx Proposal: Client Proposal and Sprint 1 Plan.docx Note for next role: Work on the Planning from Proposal.
D1l7YLB_W0qIf8fFII7EkcgAOECA | [PROJECT PROTOTYPING] - Supervisor Meeting : 30 | Done |  | Completed | Medium | Hiep Vu;Kieran Chau;Marcell Joe Sugianto;Rhys Carroll;Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-10 | 2026-08-13 | 2026-08-13 |  | false | 2026-08-13 | Khac Tung Lam Nguyen | 4/4 | Schedule the meeting;Initial understanding of project scope;Academic expectations;Team introduction | PM;UX;DEV;BA;Sprint 1 | Meet with supervisor and discuss about items list in Agenda. Done: Introduction about each member to supervisor and get academic expectations. Deliverable: Meeting Minutes: 2026-08-13_Supervisor Meeting Session.docx Note for next role: None
KWKDsjPBykOZJD7EvIkpYsgACdCE | [PROJECT PROTOTYPING] - Sprint 1 Planning : 120 | Done |  | Completed | Medium | Hiep Vu;Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-10 | 2026-08-15 | 2026-08-14 |  | false | 2026-08-15 | Khac Tung Lam Nguyen | 2/2 | Update new Planner to reflect this plan;Allocate tasks to members for the first sprint | PM;BA;Sprint 1 | Allocate every task for the Design & Bootstrap sprint across your team, week by week. Every task must sit on either the Infrastructure track or the Design/Product track, Sprint 1 has no working features on either track. The tracks are here only to help you separate things with more granularity. Done: All tasks for next sprint have been finalized and allocated. Deliverable: Plan: 13 - Telstra-muru-D Team 1 - A1_T3_Proposal.docx Note for next role: None
FW4HblnMr0CwLeiTE6s-9sgAB1_D | [PROJECT PROTOTYPING] - Project Proposal : 30 | Done |  | Completed | Medium | Hiep Vu;Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-11 | 2026-08-12 | 2026-08-10 |  | false | 2026-08-12 | Khac Tung Lam Nguyen | 2/2 | Complete Project Proposal;Notify Alessio to sign off the proposal | PM;BA | Update the Project Proposal after the Client Meeting. Done We finished the Project Proposal document. Deliverable Document is updated at Client Proposal and Sprint 1 Plan.docx Note Complete the Sprint 1 Planning once the proposal is agreed and signed off.

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
3EHNdJOPI023mvhTQzxdE8gACXL_ | [BOOTSTRAP RESTYLING] - Write requirements for team page + login styling : 60 | FoZH6yVGXEePx-q1Uhxee8gAJjtA |  | Completed | Important | 47404e3b-0183-42ad-a590-f4f87a8756bd | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-04 | 2026-08-07 | 2026-08-07 |  | false | 2026-08-07 | 502cc749-73c9-4573-b00d-32321440769c | 5/5 | Edge cases documented;Requirements shared with PM and UX;Login scope explicitly stated as styling-only;Document updated;Team page fields listed with validation/display rules | BA;Sprint 1 | Description Determine the content fields for the team page (name, photo, role, blurb) and confirm the login work is styling only, with no changes to existing auth logic or session behavior. Document edge cases such as missing photos or long blurb text. Done I wrote and finalized functional, non-functional requirements, user stories and acceptance criteria for the login page(styling-only) and team page (also edge cases). Deliverable Document is updated at https://github.com/emeralddd/capstone-boilerplate/blob/main/docs/login_restyling.docx or login_restyling.docx Note For the UX, the team branding color palette and typography are not defined yet - UX needs to confirms these before Dev start styling.
pkIqu5vHwUWaC1vjHRinZ8gAMFpO | [BOOTSTRAP RESTYLING] - Design Login Style & Team Page Layout :120 | FoZH6yVGXEePx-q1Uhxee8gAJjtA |  | Completed | Medium | 0020b81f-5d2e-4f37-909e-4180487c8765 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-04 | 2026-08-09 | 2026-08-08 |  | false | 2026-08-09 | 502cc749-73c9-4573-b00d-32321440769c | 5/5 | Document Updated;Design shared with BA for validation;Visual consistency between the two checked;Login page mockup complete;Team page mockup complete | UX;Sprint 1 | Description Produce a mockup design of the Teams and Login page. The Teams page must display all team members in a fixed order (PM, BA, UX, Dev 1, Dev 2), and each should display the name, picture, role and blurb of the member. Unavailabe information should have a placehoder in place. If the data for the members is unavailable, display "No team members yet" The login page should have a consistent style with the Teams page, and have a validation message. The pages should have responsive designs for various screen sizes Done I made a mockup design of the Teams and Login page as per sepcification, and have created some assets used in the designs. Deliverables Design: https://www.figma.com/design/JnkORkFEkRuspZS0keT8zl/Capstone?node-id=0-1&t=XG9H1VO4tKxsCIFS-1 Assets: https://www.figma.com/design/JnkORkFEkRuspZS0keT8zl/Capstone?node-id=0-1&t=XG9H1VO4tKxsCIFS-1 Note to next role The color palette used for the designs is in the "Palette" page of the FigmaDesign file. I've also pushed the assets and the design link on GitHub Asset: ./frontend/assets/ Design link: ./docs/FigmaDesign_Link.md
879IK850MEa4K9OwQP9yS8gAIEqa | [BOOTSTRAP RESTYLING]- Validate Design Against Requirements : 60 | FoZH6yVGXEePx-q1Uhxee8gAJjtA |  | Completed | Medium | 47404e3b-0183-42ad-a590-f4f87a8756bd | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-04 | 2026-08-10 | 2026-08-10 |  | false | 2026-08-10 | 502cc749-73c9-4573-b00d-32321440769c | 5/5 | Login scope confirmed unchanged;Every required field checked against the design;Design formally approved;Document Updated;Gaps (if any) sent back to UX and resolved | BA;Sprint 1 | Description Check the UX mockups against the requirements document. Confirm every field is represented, the login mockup stays styling-only, and edge cases have a visible design treatment. Flag any gaps back to UX before approving. Done I have checked UX design and validated to make sure it consistent with the requirement. Delivery Document is updated at login_restyling.docx
N7LdQjWP6E6n2h3AdqGsb8gAGYlH | [BOOTSTRAP RESTYLING] - Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only : 60 | FoZH6yVGXEePx-q1Uhxee8gAJjtA |  | Completed | Medium | 76660a01-dfb3-4982-9c26-36819353041b | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-04 | 2026-08-12 | 2026-08-12 |  | false | 2026-08-12 | 76660a01-dfb3-4982-9c26-36819353041b | 4/4 | Existing login validation/errors still function as before;No authentication logic changed;Update document;Visual style matches approved mockup | DEV;Sprint 1 | Apply the approved visual design to the existing login page in the boilerplate. Do not modify the authentication logic, validation, or session handling — styling changes only. Done: Applied the approved login styling (colors, layout, branding). Confirmed auth logic, validation, and session handling are all untouched. Styling scales to different screen sizes too. Deliverable: Branch/commit with the styling changes. Note for next role: Preexisting assets inside of frontend/components/layout/auth can be reused for teams page, team page member card had incomplete draft component created, current dashboard should be reworked into team's page and normal dashboard changed back, kept as is to keep progress. Git URL (commit): https://github.com/emeralddd/capstone-boilerplate/commit/df4749981957bca520db80d084914fbf90b42ec5
MeHPv9W4PEmKvvOAGyj1kMgAE5ZJ | [BOOTSTRAP RESTYLING]- Build Team Page & Auth Redirect : 120 | FoZH6yVGXEePx-q1Uhxee8gAJjtA |  | Completed | Medium | c8f6efb3-da65-4e5d-aa3c-30fabf9cca99 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-04 | 2026-08-13 | 2026-08-13 |  | false | 2026-08-12 | c8f6efb3-da65-4e5d-aa3c-30fabf9cca99 | 4/4 | Team page renders per design with all required fields;Successful login redirects to team page;Document updated;Team page not directly accessible without login | DEV;Sprint 1 | Build the team page per the approved design (name, member cards, blurb) and wire it so a successful login redirects the user here. The team page itself should not be reachable without a valid login. Done: Cleaned up dashboard Restyled team page per UI specification Ensured that team page is automatically redirected to after successful login, otherwise it is not accessible Deliverable: https://github.com/emeralddd/capstone-boilerplate/commit/895bb5511319a31d063a22bd2e90db4dbac72fd8 Note for next role: Team member cards are hardcoded, do we want that? And the profile photo initials are too, cannot currently put a picture inside (if that's something we want).
lGvvAuXx-kuLv7gBk4oTAsgACobb | [BOOTSTRAP RESTYLING] - Deploy - 120 | FoZH6yVGXEePx-q1Uhxee8gAJjtA |  | Completed | Medium | c8f6efb3-da65-4e5d-aa3c-30fabf9cca99 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-04 | 2026-08-13 | 2026-08-13 |  | false | 2026-08-13 | c8f6efb3-da65-4e5d-aa3c-30fabf9cca99 | 4/4 | Live URL loads without errors;Document updated;Deployment completed via boilerplate pipeline;Login → redirect → team page flow spot-checked on the deployed URL | DEV;Sprint 1 | Deploy the updated application (restyled login + team page + redirect) using the boilerplate's deployment pipeline. Confirm the deployed version is live and functioning before handing off to Dev 2. Done: Deployed website to Vercel. Deliverable: Link to website: https://capstone-boilerplate-frontend.vercel.app/ . Note for next role: None.
Oy3hDXBGnkKzwfWiCtOmdsgAGsaF | [BOOTSTRAP RESTYLING] - Test Login → Redirect → Team Page Flow : 60 | FoZH6yVGXEePx-q1Uhxee8gAJjtA |  | Completed | Medium | 76660a01-dfb3-4982-9c26-36819353041b | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-04 | 2026-08-13 | 2026-08-13 |  | false | 2026-08-13 | 76660a01-dfb3-4982-9c26-36819353041b | 4/4 | All required content verified correct and complete;Document updated;Redirect to team page confirmed;Valid login tested end-to-end on deployed URL | DEV;Sprint 1 | On the deployed URL (not localhost if possible) , test the full happy-path flow: valid login, redirect to team page, and all required content displaying correctly. Must not be the same dev who built this feature. Done: Manually tested the full happy path on the deployed URL — valid login, redirect fires, all member cards render correctly with photo/role/blurb. Note for next role: Name Rhys Carroll is spelt wrong, as "Rhys Carrol" should be "Rhys Carroll
NmKLq2vGmUm_jHzOZSUtTsgAAuUp | [BOOTSTRAP RESTYLING] - Test Edge Cases & Log Bugs : 60 | FoZH6yVGXEePx-q1Uhxee8gAJjtA |  | Completed | Medium | 76660a01-dfb3-4982-9c26-36819353041b | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-04 | 2026-08-13 | 2026-08-13 |  | false | 2026-08-13 | 76660a01-dfb3-4982-9c26-36819353041b | 5/5 | Missing-photo and long-blurb edge cases tested;Update Document;Invalid login tested;Bugs logged with repro steps, or none-found confirmed;Direct team-page access without login tested (must redirect) | DEV;Sprint 1 | Test edge cases identified by the BA: invalid login, direct team-page access without logging in, a missing photo, and an unusually long blurb. Log any bugs found back to Dev 1 with reproduction steps. Done: Tested invalid login, direct team-page URL access without login, missing-photo member, and an unusually long blurb. No bugs found. Note for next role: Unusually long blurb missing “see more” feature, just continues expanding component size.
TBxbGig6aE61zzFxCI0Pi8gAA5Do | [BOOTSTRAP RESTYLING] - Final Review & Sign-Off : 30 | FoZH6yVGXEePx-q1Uhxee8gAJjtA |  | Completed | Medium | 502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-04 | 2026-08-15 | 2026-08-15 |  | false | 2026-08-15 | 502cc749-73c9-4573-b00d-32321440769c | 3/3 | Feature reviewed end-to-end against requirements and design;All prior tasks' checklists verified complete;Task moved to Done | PM;Sprint 1 | PM reviews the completed feature end-to-end against the original requirements and design, confirms every prior task's checklist is complete, and signs off. Done: Reviewed the feature end-to-end against the requirements and design. Verified every prior task's checklist and completion comment. Everything matches — approved. Deliverable: Sign-off note. Note for next role: None — feature complete, board closed out.
8xLXAGrVbkCiy11TOMZjQsgACJTm | [BOOTSTRAP RESTYLING] - Internal Team Meeting : 30 | FoZH6yVGXEePx-q1Uhxee8gAJjtA |  | Completed | Medium | 47404e3b-0183-42ad-a590-f4f87a8756bd;c8f6efb3-da65-4e5d-aa3c-30fabf9cca99;0020b81f-5d2e-4f37-909e-4180487c8765;76660a01-dfb3-4982-9c26-36819353041b;502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-07 | 2026-08-05 | 2026-08-05 |  | false | 2026-08-07 | 502cc749-73c9-4573-b00d-32321440769c | 5/5 | Set internal deadlines for each task;Assign the tasks (especially for Dev 1 and Dev 2);Prepare for client meeting;Confirm the role for this sprint;Confirm the flow of task card on Planner | PM;UX;DEV;BA;Sprint 1 | This is the Planning Session Meeting for this sprint. Done: Introduction about each member and task assignments for demo sprint. Deliverable: Meeting Minutes: 2026-08-06_MiniSprint Planning Session.docx Note for next role: Work on each member task based on assignments.
S9Xsp7LO9UGlbeZUE8z14sgAEVWO | [PROJECT PROTOTYPING] - First Client Meeting : 30 | FoZH6yVGXEePx-q1Uhxee8gAJjtA |  | Completed | Medium | 47404e3b-0183-42ad-a590-f4f87a8756bd;c8f6efb3-da65-4e5d-aa3c-30fabf9cca99;0020b81f-5d2e-4f37-909e-4180487c8765;76660a01-dfb3-4982-9c26-36819353041b;502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-10 | 2026-08-10 | 2026-08-10 |  | false | 2026-08-11 | 502cc749-73c9-4573-b00d-32321440769c | 1/1 | Gather requirements from client | PM;UX;DEV;BA | Meet with the client to get the requirements and instructions for the project. Done: We met with Alessio to get information about the project. Deliverable: Meeting Minutes: 2026-08-10_Client Meeting Session Copy.docx Proposal: Client Proposal and Sprint 1 Plan.docx Note for next role: Work on the Planning from Proposal.
D1l7YLB_W0qIf8fFII7EkcgAOECA | [PROJECT PROTOTYPING] - Supervisor Meeting : 30 | FoZH6yVGXEePx-q1Uhxee8gAJjtA |  | Completed | Medium | 47404e3b-0183-42ad-a590-f4f87a8756bd;c8f6efb3-da65-4e5d-aa3c-30fabf9cca99;0020b81f-5d2e-4f37-909e-4180487c8765;76660a01-dfb3-4982-9c26-36819353041b;502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-10 | 2026-08-13 | 2026-08-13 |  | false | 2026-08-13 | 502cc749-73c9-4573-b00d-32321440769c | 4/4 | Schedule the meeting;Initial understanding of project scope;Academic expectations;Team introduction | PM;UX;DEV;BA;Sprint 1 | Meet with supervisor and discuss about items list in Agenda. Done: Introduction about each member to supervisor and get academic expectations. Deliverable: Meeting Minutes: 2026-08-13_Supervisor Meeting Session.docx Note for next role: None
KWKDsjPBykOZJD7EvIkpYsgACdCE | [PROJECT PROTOTYPING] - Sprint 1 Planning : 120 | FoZH6yVGXEePx-q1Uhxee8gAJjtA |  | Completed | Medium | 47404e3b-0183-42ad-a590-f4f87a8756bd;502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-10 | 2026-08-15 | 2026-08-14 |  | false | 2026-08-15 | 502cc749-73c9-4573-b00d-32321440769c | 2/2 | Update new Planner to reflect this plan;Allocate tasks to members for the first sprint | PM;BA;Sprint 1 | Allocate every task for the Design & Bootstrap sprint across your team, week by week. Every task must sit on either the Infrastructure track or the Design/Product track, Sprint 1 has no working features on either track. The tracks are here only to help you separate things with more granularity. Done: All tasks for next sprint have been finalized and allocated. Deliverable: Plan: 13 - Telstra-muru-D Team 1 - A1_T3_Proposal.docx Note for next role: None
FW4HblnMr0CwLeiTE6s-9sgAB1_D | [PROJECT PROTOTYPING] - Project Proposal : 30 | FoZH6yVGXEePx-q1Uhxee8gAJjtA |  | Completed | Medium | 47404e3b-0183-42ad-a590-f4f87a8756bd;502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-11 | 2026-08-12 | 2026-08-10 |  | false | 2026-08-12 | 502cc749-73c9-4573-b00d-32321440769c | 2/2 | Complete Project Proposal;Notify Alessio to sign off the proposal | PM;BA | Update the Project Proposal after the Client Meeting. Done We finished the Project Proposal document. Deliverable Document is updated at Client Proposal and Sprint 1 Plan.docx Note Complete the Sprint 1 Planning once the proposal is agreed and signed off.

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
oydqK3sW6USmorq7Fo9J2MgAMQdb | Blocked
PAlja3geDUK9wcgiPHXRLMgAJQF3 | Documents & Updates
61WBrw8b-ku7elPVye6LdcgAFtsD | Backlog
gU7Ym3aN5keafHDMrsJHIMgAIEiK | Doing
g3RGmcZ7ykaB5KgCntcYzMgAP19O | Reviewing
vYoBQTkjE0KgI12KqRkUNMgAL3vJ | Testing
FoZH6yVGXEePx-q1Uhxee8gAJjtA | Done
IGPitsVKvUq42DsQmwmLocgANGOu | Clean up

## Users
User ID | User Name | Email
47404e3b-0183-42ad-a590-f4f87a8756bd | Hiep Vu | S3993200@rmit.edu.vn
502cc749-73c9-4573-b00d-32321440769c | Khac Tung Lam Nguyen | S4070988@student.rmit.edu.au
0020b81f-5d2e-4f37-909e-4180487c8765 | Marcell Joe Sugianto | S4073148@student.rmit.edu.au
76660a01-dfb3-4982-9c26-36819353041b | Rhys Carroll | S3997418@student.rmit.edu.au
c8f6efb3-da65-4e5d-aa3c-30fabf9cca99 | Kieran Chau | S4090514@student.rmit.edu.au