# Client Project Proposal & Sprint 1 Plan

TEMPLATE & INSTRUCTIONS

# Instructions

This week (either Week 3 or 4), meet with your client and complete Part A — Project Proposal Summary — together with them. This is not a document you write about your client; it's a document you agree with your client. It becomes the shared reference point for what you're building.

Once Part A is agreed and signed off, complete Part B — your Sprint 1 Plan — allocating every task for the first 3 weeks of the Design & Bootstrap sprint across your team. Submit both parts as one document.

Roles on a real client team don't have to match the 5-role structure used in the in-class simulation. Combine or split roles based on what this specific project actually needs (e.g. a BA doubling as a developer, or two people on UX if the project is design-heavy). The only non-negotiable: it must be unambiguous who owns each task – PM,BA and UX tasks are not split, only one person in charge, but a BA can double up as UX.

# Understanding the 3-Sprint Structure

Every capstone project runs the same fixed arc, regardless of what you're building. You'll need to understand this before you can write the roadmap section in Part A. Things may change but overall your definition is always Initiation and Design > Core MVP Feature > Refine MVP  , for short we refer to this as ICR (Initiation, Core , Refined)

If the ICR does not fit your project, you still need to build your project around the three sprints, if this does not fit the client, please invite either Alessio or Nhi into the discussion.

### Sprint 1 — Design & Bootstrap

Two separate tracks run in parallel, not one. Infrastructure is real, not mocked — your web server, database, and storage are actually stood up and live by the end of this sprint. Product is NOT working code — designs and a paper prototype only (a digital mockup, e.g. Figma, is fine — it doesn't need to be literal paper). No working features yet, mocked or otherwise.

This sprint answers: is the plumbing live, and do we know what we're building? Not: does anything work yet.

### Sprint 2 — Core  MVP

The single main feature that proves your project's core value proposition, built end-to-end even if rough. Not polished, not complete — but a real user or client can see the idea works. This sprint answers: does the core idea actually function?

### Sprint 3 — Refine MVP

Hardening, polish, and secondary features if time allows, fixing what Sprint 2 exposed. This sprint answers: is this now presentable and closer to production-credible?

# Part A — Project Proposal Summary

## Project Details

Project name: AI Workloads & Agentic Systems in muru-D

Client / organization: muru-D Telstra

Prepared by: Group 13

Date of client discussion: 10/08/2026

## Team & Roles

List everyone on the team and what they own. Combine roles where the project calls for it — just make sure every task in Part B maps to a name here.

| Role | Assigned to | Notes |
| --- | --- | --- |
| Project Manager | Khac Tung Lam Nguyen |  |
| BA | Hiep Vu |  |
| UX | Marcell Joe Sugianto |  |
| Developer | Kieran Chau |  |
| Developer | Rhys Carroll |  |

## Problem Statement

## Telstra's muru-D Innovation Lab wants to go "from an idea all the way to a prototype much faster." Right now, turning a raw idea into something testable (a validated concept, a visual prototype, a plan) is slow and manual, and the lab wants an agentic workflow to compress that time-to-value.

## Target Users

Innovation Lab staff/innovators at muru-D (Telstra) who have early-stage product ideas, the people who'd type in "here's my idea" and need it turned into research, a refined concept, and prototype artifacts. Not end-consumers of the eventual product; the users are the Lab's own idea-generators.

## Proposed Solution

An agent-based pipeline, likely a simple website flow, or possibly a canvas-style drag-and-drop interface, where a user submits an idea, it passes through a chain of AI agents (research/discovery, to refine loop with human feedback, to generation agents), and produces outputs like a research summary, refined product statement, PowerPoint deck, visual/HTML mock-up, and a sprint plan.

## Scope Boundaries

In scope this term: An end-to-end working pipeline covering at least: idea input, research/discovery agent, refined concept (with a feedback/interview loop), one or two output-generation agents (e.g., PowerPoint slide + visual prototype). Prompt experimentation across models to justify choices (quality vs. cost).

Out of scope this term:

- Full financial/investment-grade accuracy for DVF and TAM/SAM outputs (e.g. validated market-sizing data, audited discounted cash flow models). Alessio explicitly told the team not to worry about this level of rigor; the goal is a credible first-pass automation, not analyst-grade precision.

- Automating early-stage activities beyond the two selected (DVF + TAM/SAM), later-stage outputs like PowerPoint generation, visual prototypes, or sprint planning stay out of scope this term so the team can go deep on getting two agents genuinely working, rather than shallow on many.

- A production-ready, customer-facing tool, this remains an internal prototype/proof-of-concept for muru-D's own team, not something deployed for external use.

- Formal integration or joint architecture with Team 2, both teams work independently from the same brief; no shared codebase or coordination is required this term.

## 3-Sprint Roadmap

Sprint 1 — Design & Bootstrap: Infrastructure track and product track run in parallel, the web server, database/storage, and LLM API connections are actually live and deployed, while separately the team finalizes the workflow concept (agent chain design, prompt structure plan) and produces a digital mockup/paper prototype (e.g. Figma) of the idea-input and output screens. No agent or feature is functional yet.

Sprint 2 — Raw MVP: The single core feature, idea in, pitch-ready output out, works end-to-end through the live infrastructure: a Discovery agent researches the idea, a Refine/feedback loop turns it into a clear product concept, and a presentation-generation agent turns that concept into a basic slide deck. Rough and unpolished, but a real user can input an idea and walk away with a tangible artifact proving the core value proposition.

Sprint 3 — Refine MVP: The core pipeline (idea, research, refine, artifacts) is hardened and polished based on what Sprint 2 exposed, and secondary output-generation agents (visual prototype/mock-up, sprint plan) are added if time allows, bringing the whole thing closer to something demo/production-credible.

## Success Criteria

## By end of term, from the client's perspective: a working demo where someone can input a rough idea and receive, via the agent pipeline, a refined concept plus at least one tangible artifact (e.g. slide deck or visual prototype), with documented reasoning (prompt design, model choice, cost/quality trade-offs) for why the pipeline was built the way it was.

## Something demo-ready enough to potentially feed into the showcase event.

## Assumptions & Constraints

## Team will work with Alessio as the client-side contact (not yet directly engaged in this meeting).

## RMIT/Alessio will provide LLM API access (including Claude, since Telstra already uses it) and possibly image-generation APIs, availability/limits not yet confirmed in detail.

## No fixed requirement to match Team 2's approach; both teams work from the same brief independently.

## Financial/feasibility analysis (DVF, TAM/SAM) from the original project brief is explicitly waived by Alessio, worth confirming this doesn't resurface later as a client expectation.

## Client Agreement

Client name: Alessio Bonti/Nikhita Paul

Client signature / date: [Signature / Date]

Team representative: Khac Tung Lam Nguyen

Team signature / date: Lam (11/08/2026)

# Part B — Sprint 1 Plan (Weeks 1–3)

Allocate every task for the Design & Bootstrap sprint across your team, week by week. Every task must sit on either the Infrastructure track or the Design/Product track — Sprint 1 has no working features on either track. The tracks are here only to help you separate things with more granularity. 
Remember that every team member needs to contribute 4 solid hours of work per week.

Every Developers’ tasks are Infrastructure tasks, while the rest are Design/Product tasks.

## Week 1

### BA — Business Requirements document

| Owner | Hiep | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 1.5h |

Description: Document the business case for the muru-D agentic pipeline: the problem, business objectives, target users, and success metrics, as the top-level reference the rest of Sprint 1's requirements docs build from.

Deliverable: BRD document

Acceptance criteria:

✓ Business problem and objectives clearly stated

✓ Target users (Innovation Lab idea-generators) documented

✓ Success metrics defined and consistent with the Part A proposal

### BA — Product Requirements document

| Owner | Hiep | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 1.5h |

Description: Translate the BRD into a Product Requirements Document: define product scope, the core features spanning Sprint 1-3 (chat/idea intake, research agent, output generation), and what stays out of scope this term.

Deliverable: PRD document

Acceptance criteria:

✓ Core features listed and prioritized

✓ In-scope / out-of-scope boundaries stated, aligned with Part A

✓ Shared with PM for backlog alignment

### BA — Non-functional & Functional Requirement document

| Owner | Hiep | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 2h |

Description: Break down functional requirements (what the system must do) and non-functional requirements (response time, reliability, LLM cost constraints) for the two Sprint 2 target features: chat/idea intake and the research agent.

Deliverable: Non-functional & Functional Requirement document

Acceptance criteria:

✓ Functional requirements listed per Sprint 2 feature

✓ Non-functional requirements defined (e.g. response time, cost limits)

✓ Reviewed with Dev for technical feasibility

### UX — Design system/component style guide

| Owner | Marcell | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 2h |

Description: Establish the visual foundation for the chatbot web app: colour palette, typography scale, and base component styles (buttons, inputs, cards) so Dev and UX work stay consistent from Sprint 2 onward.

Deliverable: Design system / component style guide

Acceptance criteria:

✓ Colour palette and typography defined

✓ Base component styles documented (buttons, inputs, cards, etc.)

✓ Shared with Dev for a feasibility check

### UX — User flow diagram

| Owner | Marcell | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 3h |

Description: Map the end-to-end user journey, from landing on the homepage through submitting an idea to receiving research output, supported by low-fidelity wireframes for each key screen.

Deliverable: User flow diagram with low-fidelity wireframes

Acceptance criteria:

✓ Flow covers homepage → idea input → research output

✓ Low-fidelity wireframes attached for each step

✓ Reviewed with BA for alignment with requirements

### PM — Project Charter, Roadmap

| Owner | Lam | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 2.5h |

Description: Finalize the Project Charter (objectives, scope, stakeholders, constraints) and the 3-sprint roadmap, consolidating what's already agreed in Part A into a working reference for the team.

Deliverable: Project Charter and Roadmap

Acceptance criteria:

✓ Charter covers objectives, scope, stakeholders, and constraints

✓ Roadmap reflects the ICR structure (Sprint 1/2/3) agreed with the client

✓ Shared with the full team

### PM — Risk register

| Owner | Lam | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 1h |

Description: Identify and log key risks for the sprint (e.g. LLM API access/limits not yet confirmed) with likelihood, impact, and mitigation.

Deliverable: Risk register

Acceptance criteria:

✓ At least 3-5 risks logged

✓ Each risk has likelihood, impact, and mitigation noted

✓ Register reviewed with the team

### PM — Gather documents and questions for non-tech advisors & meeting minutes

| Owner | Lam | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 1h |

Description: Compile the team's open questions and relevant documents for the non-tech advisor meeting, then write up meeting minutes afterward.

Deliverable: Documents, questions list & meeting minutes

Acceptance criteria:

✓ Questions compiled from the team beforehand

✓ Meeting minutes written and shared the same day

### PM — Tasks review & master document update

| Owner | Lam | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 0.5h |

Description: Review task progress across the team against the Sprint 1 backlog and update the master planning document to reflect current status.

Deliverable: Updated master document & tasks review

Acceptance criteria:

✓ All Week 1 tasks checked against status

✓ Master document reflects the latest status

### Dev — Git Flows

| Owner | Rhys | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 1 | Hours | 2h |

Description: Set up the git branching strategy (main/dev/feature), branch protection rules, and a baseline CI pipeline with lint checks so the team can start committing safely from Week 2.

Deliverable: Git Flows configuration & CI/lint baseline

Acceptance criteria:

✓ Branching strategy documented and applied to the repo

✓ Branch protections enabled on main

✓ CI/lint baseline runs on push/PR

### Dev — Decisions: tech stack & system architecture

| Owner | Rhys | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 1 | Hours | 2h |

Description: Evaluate and confirm the frontend/backend framework and database choices, and document the decision to build as a monolith for Sprint 1-3 given team size and timeline.

Deliverable: Decisions document

Acceptance criteria:

✓ FE, BE, and DB stack confirmed with reasoning

✓ Monolith architecture decision documented

✓ Reviewed with another Dev and PM

### Dev — Testing strategy document

| Owner | Rhys | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 1 | Hours | 1h |

Description: Outline the testing approach for Sprint 2 onward: unit tests for agent logic, integration tests for the API/DB layer, and how LLM output will be validated.

Deliverable: Testing strategy document

Acceptance criteria:

✓ Test levels defined (unit, integration)

✓ Approach for validating LLM/agent output specified

### Dev — Decisions: AI agent framework & LLM shortlist

| Owner | Kieran | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 1 | Hours | 2h |

Description: Compare agent orchestration frameworks (e.g. CrewAI, LangChain, LangGraph) for building the idea-to-research agent chain, and document the choice with reasoning.

Deliverable: Decisions document

Acceptance criteria:

✓ At least 2 frameworks compared

✓ Framework decision documented with reasoning

### Dev — Deployment option research

| Owner | Kieran | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 1 | Hours | 1h |

Description: Research deployment/hosting options (VPS, managed DB, etc.) so PM can request the right infrastructure access from muru-D/RMIT ahead of Sprint 2 build.

Deliverable: Decisions document

Acceptance criteria:

✓ Deployment options compared on cost and ease of setup

✓ Recommendation handed to PM for the client ask

### Dev — LLM shortlist, prompt test & price

| Owner | Kieran | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 1 | Hours | 2h |

Description: Shortlist candidate LLMs (including Claude, given Telstra's existing usage), run quick prompt tests against a sample idea input, and compare pricing.

Deliverable: LLM shortlist, prompt test results & pricing analysis

Acceptance criteria:

✓ At least 2 LLMs tested with sample prompts

✓ Pricing comparison documented

✓ Recommendation shared with the team

### Team — Non-tech advisor meeting

| Owner | Everyone | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 1 | Hours | 0.5h |

Description: Attend the non-tech advisor meeting to provide technical context where needed.

Deliverable: Technical input for meeting

Acceptance criteria:

✓ Meeting attended

✓ Non-technical questions answered as needed

## Week 2

### BA — USAC (Homepage, Auth)

| Owner | Hiep | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 2h |

Description: Write user stories and acceptance criteria for the five Sprint 2 features: homepage, authentication (login/logout/signup), so Dev can build directly against them.

Deliverable: USAC document for Homepage, Auth

Acceptance criteria:

✓ User stories written for all 2 features

✓ Each story has clear, testable acceptance criteria

✓ Reviewed with UX and another Dev for feasibility

### BA — USAC (Chat and Research Agents)

| Owner | Hiep | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 3h |

Description: Write user stories and acceptance criteria for the five Sprint 2 features: chat/idea intake with human-in-the-loop feedback, the research/reasoning agent chain, and save/resume chat, so Dev can build directly against them.

Deliverable: USAC document for Chat/idea, Research agent, Save/resume chat

Acceptance criteria:

✓ User stories written for all 3 features

✓ Each story has clear, testable acceptance criteria

✓ Reviewed with UX and another Dev for feasibility

### UX — UI design (Login) – clickable prototype

| Owner | Marcell | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 1h |

Description: Build a clickable Figma prototype covering login, based on Week 1's wireframes and design system.

Deliverable: Clickable prototype for login

Acceptance criteria:

✓ Screen designed at high fidelity

✓ Prototype is clickable/navigable end-to-end

✓ Uses the established design system

### UX — UI design (Chat screen) – clickable prototype

| Owner | Marcell | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 1.5h |

Description: Build a clickable Figma prototype covering the chatbot/idea-intake screen, based on Week 1's wireframes and design system.

Deliverable: Clickable prototype for chatbot

Acceptance criteria:

✓ Screen designed at high fidelity

✓ Prototype is clickable/navigable end-to-end

✓ Uses the established design system

### UX — UI design (Homepage) – clickable prototype

| Owner | Marcell | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 1.5h |

Description: Build a clickable Figma prototype covering the homepage, based on Week 1's wireframes and design system.

Deliverable: Clickable prototype for homepage

Acceptance criteria:

✓ Screen designed at high fidelity

✓ Prototype is clickable/navigable end-to-end

✓ Uses the established design system

### UX — UX Design Document

| Owner | Marcell | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 1h |

Description: Document the interaction and flow decisions behind the prototype, explaining why each screen/transition is designed the way it is, so Dev and future team members understand the reasoning.

Deliverable: UX Design Document with interaction/flow rationale

Acceptance criteria:

✓ Key interactions documented with rationale

✓ Shared with the team

### PM — SRS documents

| Owner | Lam | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 2h |

Description: Consolidate BA's USAC, UX's design docs, and Dev's architecture decisions into a Software Requirements Specification, giving the team one authoritative reference for Sprint 2 build.

Deliverable: SRS documents

Acceptance criteria:

✓ SRS consolidates USAC, design, and architecture inputs

✓ Reviewed by BA/UX/Dev leads

✓ Shared with the team

### PM — Gather documents and questions for tech advisors

| Owner | Lam | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 1h |

Description: Compile the team's technical open questions (architecture, database, LLM choice) ahead of the tech advisor meeting.

Deliverable: Documents and questions for tech advisors

Acceptance criteria:

✓ Questions compiled from the Dev team

✓ Meeting minutes attached

### PM — Tasks review & master document update

| Owner | Lam | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 0.5h |

Description: Check progress on Week 2 tasks against the backlog and flag any blockers and update master document.

Deliverable: Tasks review status

Acceptance criteria:

✓ All Week 2 tasks checked against status

✓ Master document update

### PM — Sprint 2 draft plan

| Owner | Lam | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 2 | Hours | 1h |

Description: Draft an early outline of the Sprint 2 backlog based on the USAC and architecture work completed so far, to be finalized in Week 3.

Deliverable: —

Acceptance criteria:

✓ Draft backlog covers all Sprint 2 candidate features

✓ Shared with BA for review

### Dev — System architecture diagram

| Owner | Rhys | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 2 | Hours | 3h |

Description: Diagram the system architecture: how FE, BE, database, and the agents fit together within the monolith, reflecting Week 1's tech stack decisions.

Deliverable: System architecture diagram

Acceptance criteria:

✓ Diagram covers FE, BE, DB, and the agent chain

✓ Consistent with Week 1 tech decisions

✓ Reviewed with another Dev

### Dev — APIs between BE, FE documents

| Owner | Rhys | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 2 | Hours | 2h |

Description: Document the API contract between frontend and backend, endpoints and request/response shapes, for the Sprint 2 features (chat, auth, save/resume).

Deliverable: API documentation between BE and FE

Acceptance criteria:

✓ Endpoints defined for chat, auth, and save/resume

✓ Request/response formats documented

### Dev — Database ERD and Class diagram

| Owner | Kieran | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 2 | Hours | 2.5h |

Description: Design the database entity-relationship and class diagram covering users/auth, chat sessions, idea submissions, and research agent outputs.

Deliverable: Database ERD

Acceptance criteria:

✓ ERD covers all Sprint 2 data entities (users, chats, ideas, research outputs)

✓ Class diagram aligned with the chosen tech stack

✓ Reviewed with Dev for architecture fit

### Dev — AI Agents workflow diagram

| Owner | Kieran | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 2 | Hours | 2.5h |

Description: Design the AI Agents workflow diagram.

Deliverable: AI Agents workflow diagram

Acceptance criteria:

✓ Covers all Sprint 2’s agent output.

✓ Reviewed with Dev for architecture fit

### Team — Tech advisor meeting

| Owner | Everyone | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 2 | Hours | 0.5h |

Description: Attend the tech advisor meeting to walk through the database design for feedback.

Deliverable: Technical input for meeting

Acceptance criteria:

✓ Meeting attended

✓ Feedback on diagrams

## Week 3

### BA — Use-case/Sequence diagram for Sprint 2 functions

| Owner | Hiep | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 3h |

Description: Diagram the use cases and sequence flows for Sprint 2's core functions, idea submission → research agent → feedback loop, showing how actors and system components interact step by step.

Deliverable: Usecase / Sequence diagrams for Sprint 2 key functions

Acceptance criteria:

✓ Use case diagram covers key Sprint 2 actors/functions

✓ Sequence diagram shows the idea → research → feedback flow

✓ Reviewed with Dev for technical accuracy

### BA/PM — Sprint 2 Planning

| Owner | Lam, Hiep | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 1h |

Description: Work to translate USAC and finalized requirements into a BA-side Sprint 2 task plan.

Deliverable: Next sprint plan (BA perspective)

Acceptance criteria:

✓ Sprint 2 BA tasks identified and roughly estimated

✓ Aligned with PM's overall Sprint 2 plan

### BA — UAT test case basic for Sprint 2 functions

| Owner | Hiep | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 1h |

Description: Write basic User Acceptance Test cases for Sprint 2's core functions, so testing can start as soon as features are built rather than being drafted after the fact.

Deliverable: Basic UAT test cases for Sprint 2 functions

Acceptance criteria:

✓ Test cases cover chat/idea intake and the research agent at minimum

✓ Each case has clear pass/fail criteria

### UX — Run usability test with wireframes

| Owner | Marcell | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 1h |

Description: Run a lightweight usability test of the clickable prototype with a small group to catch flow/interaction issues before Sprint 2 build starts.

Deliverable: Usability test results & feedback

Acceptance criteria:

✓ Test run with at least 2-3 participants

✓ Findings documented

### UX — Finalize design system/component style guide

| Owner | Marcell | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 2h |

Description: Incorporate Week 2 feedback and finalize the design system/component style guide as the locked reference for Sprint 2 UI build.

Deliverable: Finalized design system / component style guide

Acceptance criteria:

✓ All components/styles finalized

✓ Shared with Dev as the build reference

### UX — Accessibility/responsive check & documents

| Owner | Marcell | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 1.5h |

Description: Check the prototype against basic accessibility standards (contrast, readable text sizes) and responsive behaviour across screen sizes, and document findings.

Deliverable: Accessibility and responsive check documentation

Acceptance criteria:

✓ Contrast/accessibility checked against WCAG basics

✓ Responsive behaviour checked on at least 2 screen sizes

✓ Findings documented with any fixes needed

### PM — Gather documents and presentations for playback

| Owner | Lam | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 2h |

Description: Pull together all Sprint 1 deliverables (BRD/PRD/USAC, design docs, architecture diagrams) into a playback presentation for the client/supervisor.

Deliverable: Documents and presentation deck for playback

Acceptance criteria:

✓ Deck covers all Sprint 1 deliverables and the Sprint 2 direction

✓ Reviewed by the team before playback

### PM — Playback with supervisor and client

| Owner | Lam | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 0.5h |

Description: Present the Sprint 1 playback to the supervisor/client and capture their feedback.

Deliverable: Client playback completed & feedback recorded

Acceptance criteria:

✓ Playback delivered on schedule

✓ Feedback recorded and shared with the team

### PM — Prepare backlog for Sprint 2

| Owner | Lam | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 0.5h |

Description: Finalize the Sprint 2 backlog with tasks from BA, UX, and Dev, ready for kickoff.

Deliverable: Prepared backlog

Acceptance criteria:

✓ Backlog includes tasks from all roles

✓ Every task has owners

### PM — Tasks review and master document update

| Owner | Lam | Track | Design / Product |
| --- | --- | --- | --- |
| Week | 3 | Hours | 0.5h |

Description: Final check on Week 3/Sprint 1 task completion against the backlog and update master document.

Deliverable: Tasks review status

Acceptance criteria:

✓ All Sprint 1 tasks checked against status

✓ Master document update

### Dev — Repo setup: DB schema

| Owner | Kieran | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 3 | Hours | 2h |

Description: Set up the actual repo structure with the DB schema implemented from Week 2's ERD, ready for Sprint 2 feature build.

Deliverable: Repo setup with DB schema

Acceptance criteria:

✓ DB schema implemented, matching the Week 2 ERD

✓ Repo structure documented

### Dev — Repo setup: API scaffold

| Owner | Kieran | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 3 | Hours | 2h |

Description: Set up the actual repo structure with the API scaffold/boilerplate in place, ready for Sprint 2 feature build.

Deliverable: Repo setup with API scaffold

Acceptance criteria:

✓ API scaffold/boilerplate runs locally

✓ Repo structure documented

### Dev — Setup/architecture documentation

| Owner | Rhys | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 3 | Hours | 2.5h |

Description: Write the technical setup documentation: README, environment variables, agent chain structure, and prompt templates, so Sprint 2 work can start without re-discovery.

Deliverable: Setup and architecture documentation

Acceptance criteria:

✓ README covers local setup end-to-end

✓ Env vars and agent chain/prompt structure documented

### Dev — Test infrastructure pipeline

| Owner | Rhys | Track | Infrastructure |
| --- | --- | --- | --- |
| Week | 3 | Hours | 1.5h |

Description: Run a final smoke test of the full infrastructure stack, server, database, and API scaffold, confirming everything is connected and reachable before Sprint 2 begins.

Deliverable: Test infrastructure pipeline setup

Acceptance criteria:

✓ Server, DB, and API scaffold confirmed reachable

✓ No blocking issues found