## Plan
Plan ID | Plan name | Date of export
_1r9qFY6A0CW2kYQTldTHMgACPYI | 13 - Telstra-muru-D - Team 1 | 2026-08-15

## Consolidated Data
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
9U3D2ZGAekSTCvbky-4qjsgALcEO | Labels | Documents & Updates |  | Not started | Medium |  | Khac Tung Lam Nguyen | 2026-08-12 |  |  |  | false
CvXxBFtnA0OrZkYUnefI6cgALLFK | Instructions | Documents & Updates |  | Not started | Medium |  | Khac Tung Lam Nguyen | 2026-08-12 |  |  |  | false | [5 empty] | Assign your roles Before touching anything, agree as a team who is PM, BA, UX, Dev 1, and Dev 2. Assign each task on the board to the real person doing it. If your team has fewer than five people, roles can combine. PM Creates the tasks After discussing with the reast of the team, the PM Creates the high level tasks with the description and agrees with the rest of the team on the requirements and the time it requires. You can use many techniques to estimate how long the tasks will take, assume junior level experience. For example creating a set of API end points will take 30 minutes, but a person with no knowledge may require 2 hours. This task still only counts for 30 minutes. Every student can spend up to 10 hours on the project, if a student does not know how to complete the task, this will require them to spend their own remaining time (this means that the real budget is 10 hours not 4). Planning poker can be a good way to make an estimate. (7) Planning Poker Estimation in Scrum: A Guide to Accurate Time Estimation ¦ LinkedIn Update every task as you go Move the card into your column only when you're actually starting it. Don't work ahead. Tick off each item in the Acceptance Criteria checklist as you genuinely complete it — not before. Add a completion comment before moving the card forward: what you did, where the deliverable lives, and anything the next person needs to know. Do this in the card's Notes field — chat/tagging is fine for ongoing discussion, but the handoff itself must be left in the notes. Move the card into the next bucket immediately once it's done. The board should always reflect reality, not what you'll update "later." Handoff structure Once completed make sure to add a note in the notes with your handoff Done: one line on what you actually completed. Deliverable: a link to where it lives (doc, design file, branch/commit, deployed URL). Note for next role: anything the next person needs to know before they start — assumptions you made, edge cases you handled, things you left out of scope. Follow the hard rules — no exceptions No task starts until it's in your column, or it has been assigned to you. Every completion gets a comment before the card moves. Developers never test their own code — Dev 1 builds, Dev 2 tests. The PM writes the cards and signs off last; nobody else marks a task Done.
I34wjg76XUquNmrMYSohrcgAGweA | [Project Prototype] - Business Requirements document : 90 | Backlog |  | Not started | Medium | Hiep Vu | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Success metrics defined and consistent with the Part A proposal;Business problem and objectives clearly stated;Target users (Innovation Lab idea-generators) documented | BA;Sprint 1 | Description: Document the business case for the muru-D agentic pipeline: the problem, business objectives, target users, and success metrics, as the top-level reference the rest of Sprint 1's requirements docs build from.
7-bvvx3feEWHOqxQVrRWOMgACHp8 | [Project Prototype] Project Requirements document : 90 | Backlog |  | Not started | Medium | Hiep Vu | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Shared with PM for backlog alignment;Core features listed and prioritized;In-scope / out-of-scope boundaries stated, aligned with proposal | BA;Sprint 1 | Description: Translate the BRD into a Product Requirements Document: define product scope, the core features spanning Sprint 1-3 (chat/idea intake, research agent, output generation), and what stays out of scope this term.
TVhT8JY77k6h5c0ht-E0R8gAOOqB | [Project Prototype] Non-functional & Functional Requirement document : 120 | Backlog |  | Not started | Medium | Hiep Vu | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Reviewed with Dev for technical feasibility;Non-functional requirements defined (e.g. response time, cost limits);Functional requirements listed per Sprint 2 feature | BA;Sprint 1 | Description: Break down functional requirements (what the system must do) and non-functional requirements (response time, reliability, LLM cost constraints) for the two Sprint 2 target features: chat/idea intake and the research agent.
ZaP3XwsXIUCpEyqdHP9I28gAO97u | [Project Prototype] Design system/component style : 120 | Backlog |  | Not started | Medium | Marcell Joe Sugianto | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Shared with Dev for a feasibility check;Colour palette and typography defined;Base component styles documented (buttons, inputs, cards, etc.) | UX;Sprint 1 | Description: Establish the visual foundation for the chatbot web app: colour palette, typography scale, and base component styles (buttons, inputs, cards) so Dev and UX work stay consistent from Sprint 2 onward.
1kT7hBdlSECy4j8__iUyk8gACTno | [Project Prototype] User flow diagram : 180 | Backlog |  | Not started | Medium | Marcell Joe Sugianto | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Reviewed with BA for alignment with requirements;Flow covers homepage → idea input → research output;Low-fidelity wireframes attached for each step | UX;Sprint 1 | Description: Map the end-to-end user journey, from landing on the homepage through submitting an idea to receiving research output, supported by low-fidelity wireframes for each key screen.
KM5Zh51Vr0aVCpcLAGbTD8gAOyfZ | [Governance] Project Charter, Roadmap : 150 | Backlog |  | Not started | Medium | Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Charter covers objectives, scope, stakeholders, and constraints;Roadmap reflects the ICR structure (Sprint 1/2/3) agreed with the client;Shared with the full team | PM;Sprint 1 | Description: Finalize the Project Charter (objectives, scope, stakeholders, constraints) and the 3-sprint roadmap, consolidating what's already agreed in Part A into a working reference for the team.
spdgLJaAik-kC40j1lhwN8gADOrx | [Governance] Risk register : 60 | Backlog |  | Not started | Medium | Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Register reviewed with the team;At least 3-5 risks logged;Each risk has likelihood, impact, and mitigation noted | PM;Sprint 1 | Description: Identify and log key risks for the sprint (e.g. LLM API access/limits not yet confirmed) with likelihood, impact, and mitigation.
cS9YVyGnmUuPzhh-Lga4fMgAFUP9 | [Governance] Gather documents and questions for non-tech advisors & meeting minutes : 60 | Backlog |  | Not started | Medium | Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/2 | Questions compiled from the team beforehand;Meeting minutes written and shared | PM;Sprint 1 | Description: Compile the team's open questions and relevant documents for the non-tech advisor meeting, then write up meeting minutes afterward.
1EQKEHALrUeN0UoZualqkcgAAlHJ | [Governance] Tasks review & master document update : 30 | Backlog |  | Not started | Medium | Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/2 | Master document reflects the latest status;All Week 1 tasks checked against status | PM;Sprint 1 | Description: Review task progress across the team against the Sprint 1 backlog and update the master planning document to reflect current status.
mMF5WCD23kqnoOiQjuyISMgAL81g | [Project Prototype] Git Flows : 120 | Backlog |  | Not started | Medium | Rhys Carroll | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | CI/lint baseline runs on push/PR;Branch protections enabled on main;Branching strategy documented and applied to the repo | DEV;Sprint 1 | Description: Set up the git branching strategy (main/dev/feature), branch protection rules, and a baseline CI pipeline with lint checks so the team can start committing safely from Week 2. Consider boilerplate in demo sprint as an example.
ZqkCRnfk10K1oTIvTNnqK8gABima | [Project Prototype] Decisions: tech stack (FE, BE, Database), system architecture : 120 | Backlog |  | Not started | Medium | Rhys Carroll | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Monolith architecture decision documented;Reviewed with Dev 2 and PM;FE, BE, and DB stack confirmed with reasoning | DEV;Sprint 1 | Description: Evaluate and confirm the frontend/backend framework and database choices, and document the decision to build as a monolith for Sprint 1-3 given team size and timeline.
uxpziqqwX02F_vStjCIoNsgAMhmM | [Project Prototype] Testing strategy document : 60 | Backlog |  | Not started | Medium | Rhys Carroll | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/2 | Approach for validating LLM/agent output specified;Test levels defined (unit, integration, usability, acceptance) | DEV;Sprint 1 | Description: Outline the testing approach for Sprint 2 onward: unit tests for agent logic, integration tests for the API/DB layer, and how LLM output will be validated.
5RAjrfBFqka7s3ISw47_R8gAORHy | [Research Agents] Decisions: AI Agents framework (CrewAI, LangChain, ...) : 120 | Backlog |  | Not started | Medium | Kieran Chau | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/2 | At least 2 frameworks compared;Framework decision documented with reasoning | DEV;Sprint 1 | Description: Compare agent orchestration frameworks (e.g. CrewAI, LangChain, LangGraph) for building the idea-to-research agent chain, and document the choice with reasoning.
oCrngkF6CEaDK2Pk6F4pN8gAFNO_ | [Project Prototype] Deployment option research (VPS, database, etc.) : 60 | Backlog |  | Not started | Medium | Kieran Chau | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/2 | Recommendation handed to PM for the client ask;Deployment options compared on cost and ease of setup | DEV;Sprint 1 | Description: Research deployment/hosting options (VPS, managed DB, etc.) so PM can request the right infrastructure access from muru-D/RMIT ahead of Sprint 2 build.
l_2e-zF-dkO-ITDCxFNZP8gANmnT | [Research Agents] LLM shortlist + quick prompt test + price : 120 | Backlog |  | Not started | Medium | Kieran Chau | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Pricing comparison documented;Recommendation shared with the team;At least 2 LLMs tested with sample prompts | DEV;Sprint 1 | Description: Shortlist candidate LLMs (including Claude, given Telstra's existing usage), run quick prompt tests against a sample idea input, and compare pricing. Also note the strong and weak points of each agent.
OYJiGOWRrEyi1PYgYmQhmMgAGN_o | [Governance] Non-tech advisor meeting : 30 | Backlog |  | Not started | Medium | Hiep Vu;Marcell Joe Sugianto;Rhys Carroll;Khac Tung Lam Nguyen;Kieran Chau | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/2 | Meeting attended;Non-technical questions answered as needed | Everyone;Sprint 1 | Description: Attend the non-tech advisor meeting to provide technical context where needed.
3hAyppqQ5UWtv4_yqfYASMgAMkqV | [Project Prototype] USAC: Homepage, Authentication : 120 | Backlog |  | Not started | Medium | Hiep Vu | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/3 | Reviewed with UX and Dev for feasibility;Each story has clear, testable acceptance criteria;User stories written for all 2 features | BA;Sprint 1 | Description: Write user stories and acceptance criteria for the five Sprint 2 features: homepage, authentication (login/logout/signup), so Dev can build directly against them.
FvwWK3RhVkqGtTG3a8d7FcgALYpr | [Project Prototype] USAC: Chat and Research Agents : 180 | Backlog |  | Not started | Medium | Hiep Vu | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/3 | User stories written for all 3 features;Reviewed with UX and Dev for feasibility;Each story has clear, testable acceptance criteria | BA;Sprint 1 | Description: Write user stories and acceptance criteria for the five Sprint 2 features: chat/idea intake with human-in-the-loop feedback, the research/reasoning agent chain, and save/resume chat, so Dev can build directly against them.
DLFEEnnYgk-_nRvj4bGz3sgAMQE1 | [Project Prototype] UI design (login) – clickable prototype : 60 | Backlog |  | Not started | Medium | Marcell Joe Sugianto | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/3 | Prototype is clickable/navigable end-to-end;Screen designed at high fidelity;Uses the established design system | UX;Sprint 1 | Description: Build a clickable Figma prototype covering login, based on Week 1's wireframes and design system
TBsBnBlSOkuhoC_Qy-dR7cgALI9Y | [Project Prototype] UI design (chat screen) – clickable prototype : 90 | Backlog |  | Not started | Medium | Marcell Joe Sugianto | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/3 | Prototype is clickable/navigable end-to-end;Screen designed at high fidelity;Uses the established design system | UX;Sprint 1 | Description: Build a clickable Figma prototype covering the chatbot/idea-intake screen, based on Week 1's wireframes and design system.
-OwwWKW_nUKq_O2SGQMnN8gAGM8o | [Project Prototype] UI design (homepage) – clickable prototype : 90 | Backlog |  | Not started | Medium | Marcell Joe Sugianto | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/3 | Uses the established design system;Prototype is clickable/navigable end-to-end;Screen designed at high fidelity | UX;Sprint 1 | Description: Build a clickable Figma prototype covering the homepage, based on Week 1's wireframes and design system.
9ZTjtRIaX0StdbH1GvZeTMgAKnhx | [Project Prototype] UX Design Document : 60 | Backlog |  | Not started | Medium | Marcell Joe Sugianto | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/2 | Shared with the team;Key interactions documented with rationale | UX;Sprint 1 | Description: Document the interaction and flow decisions behind the prototype, explaining why each screen/transition is designed the way it is, so Dev and future team members understand the reasoning.
cTsePMReOUKS31jgufTAJ8gAMtta | [Governance] SRS documents : 120 | Backlog |  | Not started | Medium | Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/3 | Reviewed by BA/UX/Dev leads;SRS consolidates USAC, design, and architecture inputs;Shared with the team | PM;Sprint 1 | Description: Consolidate BA's USAC, UX's design docs, and Dev's architecture decisions into a Software Requirements Specification, giving the team one authoritative reference for Sprint 2 build.
47qNjcW13k2MmS7YrfV9w8gAANQO | [Governance] Gather documents and questions for tech advisors & meeting minutes : 60 | Backlog |  | Not started | Medium | Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/2 | Questions compiled from the Dev team;Meeting minutes attached | PM;Sprint 1 | Description: Compile the team's technical open questions (architecture, database, LLM choice) ahead of the tech advisor meeting.
sc6iMqXx0EyfSlG59nnMCMgAKSY7 | [Governance] Tasks review & master document update : 30 | Backlog |  | Not started | Medium | Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-15 |  |  |  | false |  |  | 0/2 | Master document update;All Week 2 tasks checked against status | PM;Sprint 1 | Description: Check progress on Week 2 tasks against the backlog and flag any blockers and update master document.
vxEhJkGwlU64Wg2uamb2GsgAM38L | [Governance] Sprint 2 draft plan : 60 | Backlog |  | Not started | Medium | Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-15 |  |  |  | false |  |  | 0/2 | Shared with BA for review;Draft backlog covers all Sprint 2 candidate features | PM;Sprint 1 | Description: Draft an early outline of the Sprint 2 backlog based on the USAC and architecture work completed so far, to be finalized in Week 3
ZqbFjCyRZky2_9NVboRfqcgAA-xH | [Project Prototype] System architecture diagram : 180 | Backlog |  | Not started | Medium | Rhys Carroll | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/3 | Reviewed with Dev 2;Consistent with Week 1 tech decisions;Diagram covers FE, BE, DB, and the agent | DEV;Sprint 1 | Description: Diagram the system architecture: how FE, BE, database, and the agents fit together within the monolith, reflecting Week 1's tech stack decisions
GSRkSVFDXEGkvaomfXqNO8gAPlc3 | [Project Prototype] APIs between BE, FE documents : 120 | Backlog |  | Not started | Medium | Rhys Carroll | Khac Tung Lam Nguyen | 2026-08-15 |  |  |  | false |  |  | 0/2 | Request/response formats documented;Endpoints defined for chat, auth, and save/resume | DEV;Sprint 1 | Description: Document the API contract between frontend and backend, endpoints and request/response shapes, for the Sprint 2 features (chat, auth, save/resume).
s4EEpBgZQ0qnQ6NV82t4XcgAEdWU | [Project Prototype] Database ERD, class diagram : 150 | Backlog |  | Not started | Medium | Kieran Chau | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/3 | ERD covers all Sprint 2 data entities (users, chats, ideas, research outputs);Class diagram aligned with the chosen tech stack;Reviewed with Dev 1 for architecture fit | DEV;Sprint 1 | Description: Design the database entity-relationship and class diagram covering users/auth, chat sessions, idea submissions, and research agent outputs
VmnnFEWGVkyNevZmhzlFhcgAFUU5 | [Project Prototype] AI Agents workflow diagram : 150 | Backlog |  | Not started | Medium | Kieran Chau | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/2 | Reviewed with Dev 1 for architecture fit;Covers all Sprint 2’s agent output | DEV;Sprint 1 | Description: Design the AI Agents workflow diagram
VEIQfnxhi0O7tDhYIOUufcgAGRA4 | [Governance] Tech advisor meeting : 30 | Backlog |  | Not started | Medium | Hiep Vu;Kieran Chau;Marcell Joe Sugianto;Khac Tung Lam Nguyen;Rhys Carroll | Khac Tung Lam Nguyen | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/2 | Feedback on diagrams;Meeting attended | Everyone;Sprint 1 | Description: Attend the tech advisor meeting to walk through the database design for feedback.
RRrBB6aF0kKEd50yYqbDssgABpEx | [Research Agents] Usecase/Sequence diagram for key functions in Sprint 2 : 180 | Backlog |  | Not started | Medium | Hiep Vu | Khac Tung Lam Nguyen | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/3 | Reviewed with Dev for technical accuracy;Use case diagram covers key Sprint 2 actors/functions;Sequence diagram shows the idea → research → feedback flow | BA;Sprint 1 | Description: Diagram the use cases and sequence flows for Sprint 2's core functions, idea submission → research agent → feedback loop, showing how actors and system components interact step by step
D9fsC-sKWkWTHLBoyxyhkMgAIntM | [Governance] Sprint 2 Planning : 60 | Backlog |  | Not started | Medium | Khac Tung Lam Nguyen;Hiep Vu | Khac Tung Lam Nguyen | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | Aligned with overall Sprint 2 plan;Sprint 2 tasks identified and roughly estimated | PM;BA;Sprint 1 | Description: Work to translate USAC and finalized requirements into a BA-side Sprint 2 task plan.
bohDtuosckWWKlQ2o81XF8gAHpD5 | [Governance] UAT test case basic for Sprint 2 functions : 60 | Backlog |  | Not started | Medium | Hiep Vu | Khac Tung Lam Nguyen | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | Each case has clear pass/fail criteria;Test cases cover chat/idea intake and the research agent at minimum | BA;Sprint 1 | Description: Write basic User Acceptance Test cases for Sprint 2's core functions, so testing can start as soon as features are built rather than being drafted after the fact.
QLYut3VyEU2_B6A0LbaLmMgAJXmp | [Project Prototype] Run usability test with wireframes : 60 | Backlog |  | Not started | Medium | Marcell Joe Sugianto | Khac Tung Lam Nguyen | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | Findings documented;Test run with at least 2-3 participants | UX;Sprint 1 | Description: Run a lightweight usability test of the clickable prototype with a small group to catch flow/interaction issues before Sprint 2 build starts.
b79YnmnfUUiwlrl-j3zeFcgAM4O1 | [Project Prototype] Finalize design system/component style guide : 120 | Backlog |  | Not started | Medium | Marcell Joe Sugianto | Khac Tung Lam Nguyen | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | All components/styles finalized;Shared with Dev as the build reference | UX;Sprint 1 | Description: Incorporate Week 2 feedback and finalize the design system/component style guide as the locked reference for Sprint 2 UI build.
_tSlUTqNLkW7E7cu3k3f-cgAHUe5 | [Project Prototype] Accessibility/responsive check & documents : 90 | Backlog |  | Not started | Medium | Marcell Joe Sugianto | Khac Tung Lam Nguyen | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/3 | Responsive behaviour checked on at least 2 screen sizes;Findings documented with any fixes needed;Contrast/accessibility checked against WCAG basics | UX;Sprint 1 | Description: Check the prototype against basic accessibility standards (contrast, readable text sizes) and responsive behaviour across screen sizes, and document findings.
4X52Vnf6Hkad5iK4I9wjmsgAFEX5 | [Governance] Gather documents and presentations for playback : 120 | Backlog |  | Not started | Medium | Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | Reviewed by the team before playback;Deck covers all Sprint 1 deliverables and the Sprint 2 direction | PM;Sprint 1 | Description: Pull together all Sprint 1 deliverables (BRD/PRD/USAC, design docs, architecture diagrams) into a playback presentation for the client/supervisor.
LOO4tqztBUulwKinWvuo7MgAJGVl | [Governance] Playback with supervisor and client : 30 | Backlog |  | Not started | Medium | Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | Feedback recorded and shared with the team;Playback delivered on schedule | PM;Sprint 1 | Description: Present the Sprint 1 playback to the supervisor/client and capture their feedback.
uF2ZHBfhfkOGXq4ikmdMRcgAAMWj | [Governance] Prepare backlog for Sprint 2 : 30 | Backlog |  | Not started | Medium | Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | Every task has owners;Backlog includes tasks from all roles | PM;Sprint 1 | Description: Finalize the Sprint 2 backlog with tasks from BA, UX, and Dev, ready for kickoff.
_V6EdYZFW0CcLe_1It7DSMgAAN_s | [Governance] Tasks review and master document update : 30 | Backlog |  | Not started | Medium | Khac Tung Lam Nguyen | Khac Tung Lam Nguyen | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | All Sprint 1 tasks checked against status;Master document update | PM;Sprint 1 | Description: Final check on Week 3/Sprint 1 task completion against the backlog and update master document.
MNVnsV-UlE-z8rk8_VxGI8gAOSVa | [Project Prototype] Repo setup - DB schema : 120 | Backlog |  | Not started | Medium | Kieran Chau | Khac Tung Lam Nguyen | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | DB schema implemented, matching the Week 2 ERD;Repo structure documented | DEV;Sprint 1 | Description: Set up the actual repo structure with the DB schema implemented from Week 2's ERD, ready for Sprint 2 feature build.
moQCYKuqCk6ogp94OSw3wcgANYPE | [Project Prototype] Repo setup - API scaffold : 120 | Backlog |  | Not started | Medium | Kieran Chau | Khac Tung Lam Nguyen | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | Repo structure documented;API scaffold/boilerplate runs locally | DEV;Sprint 1 | Description: Set up the actual repo structure with the API scaffold/boilerplate in place, ready for Sprint 2 feature build.
Y3D0ieQ16UiwFBxDPtai_MgAHhkx | [Project Prototype] Setup/architecture documentation (README, env vars, agent chain, prompt structure) : 150 | Backlog |  | Not started | Medium | Rhys Carroll | Khac Tung Lam Nguyen | 2026-08-15 |  |  |  | false |  |  | 0/2 | README covers local setup end-to-end;Env vars and agent chain/prompt structure documented | DEV;Sprint 1 | Description: Write the technical setup documentation: README, environment variables, agent chain structure, and prompt templates, so Sprint 2 work can start without re-discovery.
qkJXJ46JJEqp4tHMJuQPeMgABy1d | [Project Prototype] Test infrastructure pipeline : 90 | Backlog |  | Not started | Medium | Rhys Carroll | Khac Tung Lam Nguyen | 2026-08-15 |  |  |  | false |  |  | 0/2 | No blocking issues found;Server, DB, and API scaffold confirmed reachable | DEV;Sprint 1 | Description: Run a final smoke test of the full infrastructure stack, server, database, and API scaffold, confirming everything is connected and reachable before Sprint 2 begins

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
9U3D2ZGAekSTCvbky-4qjsgALcEO | Labels | 9REwgKhAyEWsD3-L2mVAH8gAPgjV |  | Not started | Medium |  | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-12 |  |  |  | false
CvXxBFtnA0OrZkYUnefI6cgALLFK | Instructions | 9REwgKhAyEWsD3-L2mVAH8gAPgjV |  | Not started | Medium |  | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-12 |  |  |  | false | [5 empty] | Assign your roles Before touching anything, agree as a team who is PM, BA, UX, Dev 1, and Dev 2. Assign each task on the board to the real person doing it. If your team has fewer than five people, roles can combine. PM Creates the tasks After discussing with the reast of the team, the PM Creates the high level tasks with the description and agrees with the rest of the team on the requirements and the time it requires. You can use many techniques to estimate how long the tasks will take, assume junior level experience. For example creating a set of API end points will take 30 minutes, but a person with no knowledge may require 2 hours. This task still only counts for 30 minutes. Every student can spend up to 10 hours on the project, if a student does not know how to complete the task, this will require them to spend their own remaining time (this means that the real budget is 10 hours not 4). Planning poker can be a good way to make an estimate. (7) Planning Poker Estimation in Scrum: A Guide to Accurate Time Estimation ¦ LinkedIn Update every task as you go Move the card into your column only when you're actually starting it. Don't work ahead. Tick off each item in the Acceptance Criteria checklist as you genuinely complete it — not before. Add a completion comment before moving the card forward: what you did, where the deliverable lives, and anything the next person needs to know. Do this in the card's Notes field — chat/tagging is fine for ongoing discussion, but the handoff itself must be left in the notes. Move the card into the next bucket immediately once it's done. The board should always reflect reality, not what you'll update "later." Handoff structure Once completed make sure to add a note in the notes with your handoff Done: one line on what you actually completed. Deliverable: a link to where it lives (doc, design file, branch/commit, deployed URL). Note for next role: anything the next person needs to know before they start — assumptions you made, edge cases you handled, things you left out of scope. Follow the hard rules — no exceptions No task starts until it's in your column, or it has been assigned to you. Every completion gets a comment before the card moves. Developers never test their own code — Dev 1 builds, Dev 2 tests. The PM writes the cards and signs off last; nobody else marks a task Done.
I34wjg76XUquNmrMYSohrcgAGweA | [Project Prototype] - Business Requirements document : 90 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 47404e3b-0183-42ad-a590-f4f87a8756bd | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Success metrics defined and consistent with the Part A proposal;Business problem and objectives clearly stated;Target users (Innovation Lab idea-generators) documented | BA;Sprint 1 | Description: Document the business case for the muru-D agentic pipeline: the problem, business objectives, target users, and success metrics, as the top-level reference the rest of Sprint 1's requirements docs build from.
7-bvvx3feEWHOqxQVrRWOMgACHp8 | [Project Prototype] Project Requirements document : 90 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 47404e3b-0183-42ad-a590-f4f87a8756bd | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Shared with PM for backlog alignment;Core features listed and prioritized;In-scope / out-of-scope boundaries stated, aligned with proposal | BA;Sprint 1 | Description: Translate the BRD into a Product Requirements Document: define product scope, the core features spanning Sprint 1-3 (chat/idea intake, research agent, output generation), and what stays out of scope this term.
TVhT8JY77k6h5c0ht-E0R8gAOOqB | [Project Prototype] Non-functional & Functional Requirement document : 120 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 47404e3b-0183-42ad-a590-f4f87a8756bd | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Reviewed with Dev for technical feasibility;Non-functional requirements defined (e.g. response time, cost limits);Functional requirements listed per Sprint 2 feature | BA;Sprint 1 | Description: Break down functional requirements (what the system must do) and non-functional requirements (response time, reliability, LLM cost constraints) for the two Sprint 2 target features: chat/idea intake and the research agent.
ZaP3XwsXIUCpEyqdHP9I28gAO97u | [Project Prototype] Design system/component style : 120 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 0020b81f-5d2e-4f37-909e-4180487c8765 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Shared with Dev for a feasibility check;Colour palette and typography defined;Base component styles documented (buttons, inputs, cards, etc.) | UX;Sprint 1 | Description: Establish the visual foundation for the chatbot web app: colour palette, typography scale, and base component styles (buttons, inputs, cards) so Dev and UX work stay consistent from Sprint 2 onward.
1kT7hBdlSECy4j8__iUyk8gACTno | [Project Prototype] User flow diagram : 180 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 0020b81f-5d2e-4f37-909e-4180487c8765 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Reviewed with BA for alignment with requirements;Flow covers homepage → idea input → research output;Low-fidelity wireframes attached for each step | UX;Sprint 1 | Description: Map the end-to-end user journey, from landing on the homepage through submitting an idea to receiving research output, supported by low-fidelity wireframes for each key screen.
KM5Zh51Vr0aVCpcLAGbTD8gAOyfZ | [Governance] Project Charter, Roadmap : 150 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Charter covers objectives, scope, stakeholders, and constraints;Roadmap reflects the ICR structure (Sprint 1/2/3) agreed with the client;Shared with the full team | PM;Sprint 1 | Description: Finalize the Project Charter (objectives, scope, stakeholders, constraints) and the 3-sprint roadmap, consolidating what's already agreed in Part A into a working reference for the team.
spdgLJaAik-kC40j1lhwN8gADOrx | [Governance] Risk register : 60 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Register reviewed with the team;At least 3-5 risks logged;Each risk has likelihood, impact, and mitigation noted | PM;Sprint 1 | Description: Identify and log key risks for the sprint (e.g. LLM API access/limits not yet confirmed) with likelihood, impact, and mitigation.
cS9YVyGnmUuPzhh-Lga4fMgAFUP9 | [Governance] Gather documents and questions for non-tech advisors & meeting minutes : 60 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/2 | Questions compiled from the team beforehand;Meeting minutes written and shared | PM;Sprint 1 | Description: Compile the team's open questions and relevant documents for the non-tech advisor meeting, then write up meeting minutes afterward.
1EQKEHALrUeN0UoZualqkcgAAlHJ | [Governance] Tasks review & master document update : 30 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/2 | Master document reflects the latest status;All Week 1 tasks checked against status | PM;Sprint 1 | Description: Review task progress across the team against the Sprint 1 backlog and update the master planning document to reflect current status.
mMF5WCD23kqnoOiQjuyISMgAL81g | [Project Prototype] Git Flows : 120 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 76660a01-dfb3-4982-9c26-36819353041b | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | CI/lint baseline runs on push/PR;Branch protections enabled on main;Branching strategy documented and applied to the repo | DEV;Sprint 1 | Description: Set up the git branching strategy (main/dev/feature), branch protection rules, and a baseline CI pipeline with lint checks so the team can start committing safely from Week 2. Consider boilerplate in demo sprint as an example.
ZqkCRnfk10K1oTIvTNnqK8gABima | [Project Prototype] Decisions: tech stack (FE, BE, Database), system architecture : 120 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 76660a01-dfb3-4982-9c26-36819353041b | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Monolith architecture decision documented;Reviewed with Dev 2 and PM;FE, BE, and DB stack confirmed with reasoning | DEV;Sprint 1 | Description: Evaluate and confirm the frontend/backend framework and database choices, and document the decision to build as a monolith for Sprint 1-3 given team size and timeline.
uxpziqqwX02F_vStjCIoNsgAMhmM | [Project Prototype] Testing strategy document : 60 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 76660a01-dfb3-4982-9c26-36819353041b | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/2 | Approach for validating LLM/agent output specified;Test levels defined (unit, integration, usability, acceptance) | DEV;Sprint 1 | Description: Outline the testing approach for Sprint 2 onward: unit tests for agent logic, integration tests for the API/DB layer, and how LLM output will be validated.
5RAjrfBFqka7s3ISw47_R8gAORHy | [Research Agents] Decisions: AI Agents framework (CrewAI, LangChain, ...) : 120 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | c8f6efb3-da65-4e5d-aa3c-30fabf9cca99 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/2 | At least 2 frameworks compared;Framework decision documented with reasoning | DEV;Sprint 1 | Description: Compare agent orchestration frameworks (e.g. CrewAI, LangChain, LangGraph) for building the idea-to-research agent chain, and document the choice with reasoning.
oCrngkF6CEaDK2Pk6F4pN8gAFNO_ | [Project Prototype] Deployment option research (VPS, database, etc.) : 60 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | c8f6efb3-da65-4e5d-aa3c-30fabf9cca99 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/2 | Recommendation handed to PM for the client ask;Deployment options compared on cost and ease of setup | DEV;Sprint 1 | Description: Research deployment/hosting options (VPS, managed DB, etc.) so PM can request the right infrastructure access from muru-D/RMIT ahead of Sprint 2 build.
l_2e-zF-dkO-ITDCxFNZP8gANmnT | [Research Agents] LLM shortlist + quick prompt test + price : 120 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | c8f6efb3-da65-4e5d-aa3c-30fabf9cca99 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/3 | Pricing comparison documented;Recommendation shared with the team;At least 2 LLMs tested with sample prompts | DEV;Sprint 1 | Description: Shortlist candidate LLMs (including Claude, given Telstra's existing usage), run quick prompt tests against a sample idea input, and compare pricing. Also note the strong and weak points of each agent.
OYJiGOWRrEyi1PYgYmQhmMgAGN_o | [Governance] Non-tech advisor meeting : 30 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 47404e3b-0183-42ad-a590-f4f87a8756bd;0020b81f-5d2e-4f37-909e-4180487c8765;76660a01-dfb3-4982-9c26-36819353041b;502cc749-73c9-4573-b00d-32321440769c;c8f6efb3-da65-4e5d-aa3c-30fabf9cca99 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-21 |  |  | false |  |  | 0/2 | Meeting attended;Non-technical questions answered as needed | Everyone;Sprint 1 | Description: Attend the non-tech advisor meeting to provide technical context where needed.
3hAyppqQ5UWtv4_yqfYASMgAMkqV | [Project Prototype] USAC: Homepage, Authentication : 120 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 47404e3b-0183-42ad-a590-f4f87a8756bd | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/3 | Reviewed with UX and Dev for feasibility;Each story has clear, testable acceptance criteria;User stories written for all 2 features | BA;Sprint 1 | Description: Write user stories and acceptance criteria for the five Sprint 2 features: homepage, authentication (login/logout/signup), so Dev can build directly against them.
FvwWK3RhVkqGtTG3a8d7FcgALYpr | [Project Prototype] USAC: Chat and Research Agents : 180 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 47404e3b-0183-42ad-a590-f4f87a8756bd | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/3 | User stories written for all 3 features;Reviewed with UX and Dev for feasibility;Each story has clear, testable acceptance criteria | BA;Sprint 1 | Description: Write user stories and acceptance criteria for the five Sprint 2 features: chat/idea intake with human-in-the-loop feedback, the research/reasoning agent chain, and save/resume chat, so Dev can build directly against them.
DLFEEnnYgk-_nRvj4bGz3sgAMQE1 | [Project Prototype] UI design (login) – clickable prototype : 60 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 0020b81f-5d2e-4f37-909e-4180487c8765 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/3 | Prototype is clickable/navigable end-to-end;Screen designed at high fidelity;Uses the established design system | UX;Sprint 1 | Description: Build a clickable Figma prototype covering login, based on Week 1's wireframes and design system
TBsBnBlSOkuhoC_Qy-dR7cgALI9Y | [Project Prototype] UI design (chat screen) – clickable prototype : 90 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 0020b81f-5d2e-4f37-909e-4180487c8765 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/3 | Prototype is clickable/navigable end-to-end;Screen designed at high fidelity;Uses the established design system | UX;Sprint 1 | Description: Build a clickable Figma prototype covering the chatbot/idea-intake screen, based on Week 1's wireframes and design system.
-OwwWKW_nUKq_O2SGQMnN8gAGM8o | [Project Prototype] UI design (homepage) – clickable prototype : 90 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 0020b81f-5d2e-4f37-909e-4180487c8765 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/3 | Uses the established design system;Prototype is clickable/navigable end-to-end;Screen designed at high fidelity | UX;Sprint 1 | Description: Build a clickable Figma prototype covering the homepage, based on Week 1's wireframes and design system.
9ZTjtRIaX0StdbH1GvZeTMgAKnhx | [Project Prototype] UX Design Document : 60 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 0020b81f-5d2e-4f37-909e-4180487c8765 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/2 | Shared with the team;Key interactions documented with rationale | UX;Sprint 1 | Description: Document the interaction and flow decisions behind the prototype, explaining why each screen/transition is designed the way it is, so Dev and future team members understand the reasoning.
cTsePMReOUKS31jgufTAJ8gAMtta | [Governance] SRS documents : 120 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/3 | Reviewed by BA/UX/Dev leads;SRS consolidates USAC, design, and architecture inputs;Shared with the team | PM;Sprint 1 | Description: Consolidate BA's USAC, UX's design docs, and Dev's architecture decisions into a Software Requirements Specification, giving the team one authoritative reference for Sprint 2 build.
47qNjcW13k2MmS7YrfV9w8gAANQO | [Governance] Gather documents and questions for tech advisors & meeting minutes : 60 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/2 | Questions compiled from the Dev team;Meeting minutes attached | PM;Sprint 1 | Description: Compile the team's technical open questions (architecture, database, LLM choice) ahead of the tech advisor meeting.
sc6iMqXx0EyfSlG59nnMCMgAKSY7 | [Governance] Tasks review & master document update : 30 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 |  |  |  | false |  |  | 0/2 | Master document update;All Week 2 tasks checked against status | PM;Sprint 1 | Description: Check progress on Week 2 tasks against the backlog and flag any blockers and update master document.
vxEhJkGwlU64Wg2uamb2GsgAM38L | [Governance] Sprint 2 draft plan : 60 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 |  |  |  | false |  |  | 0/2 | Shared with BA for review;Draft backlog covers all Sprint 2 candidate features | PM;Sprint 1 | Description: Draft an early outline of the Sprint 2 backlog based on the USAC and architecture work completed so far, to be finalized in Week 3
ZqbFjCyRZky2_9NVboRfqcgAA-xH | [Project Prototype] System architecture diagram : 180 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 76660a01-dfb3-4982-9c26-36819353041b | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/3 | Reviewed with Dev 2;Consistent with Week 1 tech decisions;Diagram covers FE, BE, DB, and the agent | DEV;Sprint 1 | Description: Diagram the system architecture: how FE, BE, database, and the agents fit together within the monolith, reflecting Week 1's tech stack decisions
GSRkSVFDXEGkvaomfXqNO8gAPlc3 | [Project Prototype] APIs between BE, FE documents : 120 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 76660a01-dfb3-4982-9c26-36819353041b | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 |  |  |  | false |  |  | 0/2 | Request/response formats documented;Endpoints defined for chat, auth, and save/resume | DEV;Sprint 1 | Description: Document the API contract between frontend and backend, endpoints and request/response shapes, for the Sprint 2 features (chat, auth, save/resume).
s4EEpBgZQ0qnQ6NV82t4XcgAEdWU | [Project Prototype] Database ERD, class diagram : 150 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | c8f6efb3-da65-4e5d-aa3c-30fabf9cca99 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/3 | ERD covers all Sprint 2 data entities (users, chats, ideas, research outputs);Class diagram aligned with the chosen tech stack;Reviewed with Dev 1 for architecture fit | DEV;Sprint 1 | Description: Design the database entity-relationship and class diagram covering users/auth, chat sessions, idea submissions, and research agent outputs
VmnnFEWGVkyNevZmhzlFhcgAFUU5 | [Project Prototype] AI Agents workflow diagram : 150 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | c8f6efb3-da65-4e5d-aa3c-30fabf9cca99 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/2 | Reviewed with Dev 1 for architecture fit;Covers all Sprint 2’s agent output | DEV;Sprint 1 | Description: Design the AI Agents workflow diagram
VEIQfnxhi0O7tDhYIOUufcgAGRA4 | [Governance] Tech advisor meeting : 30 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 47404e3b-0183-42ad-a590-f4f87a8756bd;c8f6efb3-da65-4e5d-aa3c-30fabf9cca99;0020b81f-5d2e-4f37-909e-4180487c8765;502cc749-73c9-4573-b00d-32321440769c;76660a01-dfb3-4982-9c26-36819353041b | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-08-28 |  |  | false |  |  | 0/2 | Feedback on diagrams;Meeting attended | Everyone;Sprint 1 | Description: Attend the tech advisor meeting to walk through the database design for feedback.
RRrBB6aF0kKEd50yYqbDssgABpEx | [Research Agents] Usecase/Sequence diagram for key functions in Sprint 2 : 180 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 47404e3b-0183-42ad-a590-f4f87a8756bd | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/3 | Reviewed with Dev for technical accuracy;Use case diagram covers key Sprint 2 actors/functions;Sequence diagram shows the idea → research → feedback flow | BA;Sprint 1 | Description: Diagram the use cases and sequence flows for Sprint 2's core functions, idea submission → research agent → feedback loop, showing how actors and system components interact step by step
D9fsC-sKWkWTHLBoyxyhkMgAIntM | [Governance] Sprint 2 Planning : 60 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 502cc749-73c9-4573-b00d-32321440769c;47404e3b-0183-42ad-a590-f4f87a8756bd | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | Aligned with overall Sprint 2 plan;Sprint 2 tasks identified and roughly estimated | PM;BA;Sprint 1 | Description: Work to translate USAC and finalized requirements into a BA-side Sprint 2 task plan.
bohDtuosckWWKlQ2o81XF8gAHpD5 | [Governance] UAT test case basic for Sprint 2 functions : 60 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 47404e3b-0183-42ad-a590-f4f87a8756bd | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | Each case has clear pass/fail criteria;Test cases cover chat/idea intake and the research agent at minimum | BA;Sprint 1 | Description: Write basic User Acceptance Test cases for Sprint 2's core functions, so testing can start as soon as features are built rather than being drafted after the fact.
QLYut3VyEU2_B6A0LbaLmMgAJXmp | [Project Prototype] Run usability test with wireframes : 60 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 0020b81f-5d2e-4f37-909e-4180487c8765 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | Findings documented;Test run with at least 2-3 participants | UX;Sprint 1 | Description: Run a lightweight usability test of the clickable prototype with a small group to catch flow/interaction issues before Sprint 2 build starts.
b79YnmnfUUiwlrl-j3zeFcgAM4O1 | [Project Prototype] Finalize design system/component style guide : 120 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 0020b81f-5d2e-4f37-909e-4180487c8765 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | All components/styles finalized;Shared with Dev as the build reference | UX;Sprint 1 | Description: Incorporate Week 2 feedback and finalize the design system/component style guide as the locked reference for Sprint 2 UI build.
_tSlUTqNLkW7E7cu3k3f-cgAHUe5 | [Project Prototype] Accessibility/responsive check & documents : 90 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 0020b81f-5d2e-4f37-909e-4180487c8765 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/3 | Responsive behaviour checked on at least 2 screen sizes;Findings documented with any fixes needed;Contrast/accessibility checked against WCAG basics | UX;Sprint 1 | Description: Check the prototype against basic accessibility standards (contrast, readable text sizes) and responsive behaviour across screen sizes, and document findings.
4X52Vnf6Hkad5iK4I9wjmsgAFEX5 | [Governance] Gather documents and presentations for playback : 120 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | Reviewed by the team before playback;Deck covers all Sprint 1 deliverables and the Sprint 2 direction | PM;Sprint 1 | Description: Pull together all Sprint 1 deliverables (BRD/PRD/USAC, design docs, architecture diagrams) into a playback presentation for the client/supervisor.
LOO4tqztBUulwKinWvuo7MgAJGVl | [Governance] Playback with supervisor and client : 30 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | Feedback recorded and shared with the team;Playback delivered on schedule | PM;Sprint 1 | Description: Present the Sprint 1 playback to the supervisor/client and capture their feedback.
uF2ZHBfhfkOGXq4ikmdMRcgAAMWj | [Governance] Prepare backlog for Sprint 2 : 30 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | Every task has owners;Backlog includes tasks from all roles | PM;Sprint 1 | Description: Finalize the Sprint 2 backlog with tasks from BA, UX, and Dev, ready for kickoff.
_V6EdYZFW0CcLe_1It7DSMgAAN_s | [Governance] Tasks review and master document update : 30 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 502cc749-73c9-4573-b00d-32321440769c | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | All Sprint 1 tasks checked against status;Master document update | PM;Sprint 1 | Description: Final check on Week 3/Sprint 1 task completion against the backlog and update master document.
MNVnsV-UlE-z8rk8_VxGI8gAOSVa | [Project Prototype] Repo setup - DB schema : 120 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | c8f6efb3-da65-4e5d-aa3c-30fabf9cca99 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | DB schema implemented, matching the Week 2 ERD;Repo structure documented | DEV;Sprint 1 | Description: Set up the actual repo structure with the DB schema implemented from Week 2's ERD, ready for Sprint 2 feature build.
moQCYKuqCk6ogp94OSw3wcgANYPE | [Project Prototype] Repo setup - API scaffold : 120 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | c8f6efb3-da65-4e5d-aa3c-30fabf9cca99 | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 | 2026-09-04 |  |  | false |  |  | 0/2 | Repo structure documented;API scaffold/boilerplate runs locally | DEV;Sprint 1 | Description: Set up the actual repo structure with the API scaffold/boilerplate in place, ready for Sprint 2 feature build.
Y3D0ieQ16UiwFBxDPtai_MgAHhkx | [Project Prototype] Setup/architecture documentation (README, env vars, agent chain, prompt structure) : 150 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 76660a01-dfb3-4982-9c26-36819353041b | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 |  |  |  | false |  |  | 0/2 | README covers local setup end-to-end;Env vars and agent chain/prompt structure documented | DEV;Sprint 1 | Description: Write the technical setup documentation: README, environment variables, agent chain structure, and prompt templates, so Sprint 2 work can start without re-discovery.
qkJXJ46JJEqp4tHMJuQPeMgABy1d | [Project Prototype] Test infrastructure pipeline : 90 | xWiU3uCQJ06TDMmKMt-iDcgAFQ0d |  | Not started | Medium | 76660a01-dfb3-4982-9c26-36819353041b | 502cc749-73c9-4573-b00d-32321440769c | 2026-08-15 |  |  |  | false |  |  | 0/2 | No blocking issues found;Server, DB, and API scaffold confirmed reachable | DEV;Sprint 1 | Description: Run a final smoke test of the full infrastructure stack, server, database, and API scaffold, confirming everything is connected and reachable before Sprint 2 begins

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
H0T1obSyzUGCNKIQd6hFOMgAA4LH | Blocked
9REwgKhAyEWsD3-L2mVAH8gAPgjV | Documents & Updates
xWiU3uCQJ06TDMmKMt-iDcgAFQ0d | Backlog
K5ozqz2AU0afx_PVJjSFPcgAOPD4 | Doing
EGOD-54pmk65F57RHFY9EsgAGSe3 | Testing (if required)
RbTQdR_GPE2sdfZcv-712sgAG3v0 | Reviewing
hnIq2ViO7U6RcwkWB06cg8gAEr8R | Done
TxMCqUEVgUmvxsOgwHACpMgAGKKo | Clean up

## Users
User ID | User Name | Email
502cc749-73c9-4573-b00d-32321440769c | Khac Tung Lam Nguyen | S4070988@student.rmit.edu.au
47404e3b-0183-42ad-a590-f4f87a8756bd | Hiep Vu | S3993200@rmit.edu.vn
0020b81f-5d2e-4f37-909e-4180487c8765 | Marcell Joe Sugianto | S4073148@student.rmit.edu.au
76660a01-dfb3-4982-9c26-36819353041b | Rhys Carroll | S3997418@student.rmit.edu.au
c8f6efb3-da65-4e5d-aa3c-30fabf9cca99 | Kieran Chau | S4090514@student.rmit.edu.au